# Engineering Change Authority - Manufacturing Readiness Review

Readiness target date: 2026-10-31. Commercial cost review threshold: USD 15,000 per part, with a signed and approved engineering change cost per part. Authority note: Signed decisions in this document supersede planning registers, supplier quote snapshots, and outdated master-register release flags.

Precedence rules: Use signed ECO/SCR decisions for drawing revision, material grade, supplier accountability, signed cost, cycle-time adjustment, and resolved release date. Open high or critical inspection exceptions override any ready-for-release claims. Routing and capacity evidence determines machining/material hold status when it conflicts with unsupported master readiness assertions. Pending supplier quote requests without signed approval are unresolved follow-up items and are not considered approved production costs.

### Signed Revision and Material Decisions

| ECO-REV-003 | MP-003 | Signed Hold | C | 42CrMo4 QT | 2026-11-05 | Engineering Hold | Master register rev B/S355JR is frozen and not release-valid. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ECO-MAT-006 | MP-006 | Signed Hold | B | 17-4PH H1150 | 2026-11-08 | Supplier Material Hold | Supplier material grade changes to H1150 bar stock; delivery after target. |
| ECO-GL-010 | MP-010 | Signed Hold | D | 42CrMo4 QT | 2026-11-12 | Engineering Hold | Signed rev D routing and release date supersede tracker date. |
| ECO-VN-016 | MP-016 | Signed Transfer | B | S355JR | 2026-11-15 | Supplier Material Hold | Accountable supplier transfers from ForgeMax to AlloyWorks after heat-treatment queue review. |
| ECO-DEF-023 | MP-023 | Signed Defer | B | AISI 304 |  | Defer | Material certificate and machine acceptance evidence are missing; no defensible release date. |
| ECO-GL-029 | MP-029 | Signed Release | C | 6082-T6 Al | 2026-10-28 | Release Ready | Fills blank master-register release date. |
| ECO-VN-041 | MP-041 | Signed Transfer | C | EN8 | 2026-10-25 | Release Ready | Accountable supplier transfers from CNC North to GuardFab after supplier handoff. |
| ECO-MAT-044 | MP-044 | Signed Hold | C | 42CrMo4 QT | 2026-11-08 | Supplier Material Hold | Heat-treatment certificate package is incomplete. |

### Signed Supplier, Cost, and Cycle Decisions

| SCR-2005 | MP-006 | Approved | 11400 | 2.0 | AlloyWorks | 2026-11-08 | Overrides supplier snapshot pending USD 10,000. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SCR-2008 | MP-009 | Rejected | 0 | 0.0 | CNC North | 2026-10-24 | Supplier approved fixture-polish claim is rejected. |
| SCR-2011 | MP-012 | Approved | 18600 | 3.5 | GuardFab | 2026-10-26 | Supplier snapshot shows rejected, but signed authority approves. |
| SCR-2014 | MP-018 | Approved | 11250 | 2.0 | AlloyWorks | 2026-11-04 | Supplier pending amount is signed by authority. |
| SCR-2019 | MP-022 | Rejected | 0 | 0.0 | ForgeMax | 2026-11-02 | Supplier approved fixture claim is rejected. |
| SCR-2020 | MP-021 | Approved | 9750 | 1.0 | CNC North | 2026-11-03 | Signed approval is missing from supplier_quote_register.csv and must still be counted. |
| SCR-2024 | MP-027 | Approved | 12600 | 2.5 | ForgeMax | 2026-10-29 | Overrides supplier amount USD 12,000. |
| SCR-2029 | MP-033 | Rejected | 0 | 0.0 | GuardFab | 2026-10-24 | Supplier approved rework claim is rejected. |
| SCR-2030 | MP-034 | Approved | 17400 | 4.0 | CNC North | 2026-10-30 | Pending supplier snapshot is signed and exceeds cost-review threshold. |

### Known Master Register Freeze Exceptions

| MP-003 | Ready for Release, Rev B, S355JR | ECO-REV-003 and routing row 4 | Engineering Hold | Master register was frozen before rev C/material decision. |
| --- | --- | --- | --- | --- |
| MP-006 | Ready for Release, material H900, machining Ready | ECO-MAT-006 and routing row 7 | Supplier Material Hold | Material delivery occurs after 2026-10-31. |
| MP-010 | Planned release 2026-10-20, Rev C | ECO-GL-010 | Engineering Hold | Signed rev D release date is 2026-11-12. |
| MP-021 | Ready for Release, FAI Accepted | Inspection exception IX-3103 | Inspection Remediation | Open high dimensional exception blocks release. |
| MP-023 | Ready for Release, power/material evidence implied Ready | ECO-DEF-023 and IX-3108 | Defer | Missing material certificate and acceptance evidence. |
| MP-039 | Ready for Release, FAI Accepted | Inspection exception IX-3112 | Inspection Remediation | Open critical weld/crack exception blocks release. |
| MP-044 | Ready for Release, way/route Ready | ECO-MAT-044 and IX-3124 | Supplier Material Hold | Heat-treatment certificate package incomplete. |
| MP-047 | Ready for Release, FAI Accepted | Inspection exception IX-3117 | Inspection Remediation | Open high slot-width exception blocks release. |

### Commercial Review and Follow-Up Notes

Parts with signed and approved engineering-change costs above USD 15,000 require a Cost Review if no higher-priority hold category applies. MP-012 and MP-034 are designated as cost-review parts based on their signed and approved amounts.

Supplier quote rows SCR-2026/MP-029, SCR-2035/MP-041, SCR-X011/MP-011, SCR-X026/MP-026, SCR-X030/MP-030, and SCR-X046/MP-046 lack signed approval. Move these items to Follow-Up and exclude them from the approved production cost.

For supplier-controlled baseline unit cost conflicts, use supplier_quote_register.csv as the finance-controlled source for cost and cycle exposure. Known baseline conflicts include MP-010, MP-021, MP-027, MP-034, and MP-041.